## Overview & Summary
SHINEX HRIS & PAYROLL SYSTEM - COMPREHENSIVE UAT SUITE
Master User Acceptance Testing (UAT) Manual Test Execution Workbook
SYSTEM & TEST ENVIRONMENT INFORMATION |  | MODULE EXECUTION SUMMARY
Project Name | Shinex Facility Management HRIS & Payroll System | Module Name | Total Test Cases | High Priority | Medium Priority | Status
Test Scope | End-to-End System Modules (Authentication, Masters, Employees, Attendance, Payroll, Reports, Admin) | 01. Authentication & Security (RBAC) | 5 | 4 | 1 | Ready
Target Release | Version 2.0 (Phase 1 & Phase 2 Enhanced) | 02. Dashboard & Scope Switcher | 4 | 2 | 2 | Ready
Environment | Local Staging / UAT (SQL Server + Spring Boot + React Vite) | 03. Employee Sections Master (Isolated / Salary Auto-fill) | 10 | 8 | 2 | Ready
Execution Lead | QA & Implementation Team | 04. Business Centers & Plant Masters | 6 | 4 | 2 | Ready
Date Created | September 30, 2026 | 05. Master Data (Additions, Deductions, BCards) | 6 | 3 | 3 | Ready
Default Sign-in | superadmin / 123 (Full SuperAdmin Scope) | 06. Employee Profile & Compensation | 10 | 8 | 2 | Ready
|  | 07. Daily Attendance & Shift Management | 8 | 6 | 2 | Ready
|  | 08. Employee Additions & Deductions Processing | 6 | 4 | 2 | Ready
|  | 09. Leave & Loan Lifecycle | 6 | 4 | 2 | Ready
|  | 10. Plant Transfers | 4 | 3 | 1 | Ready
|  | 11. Monthly Summary & Payroll Engine | 8 | 7 | 1 | Ready
|  | 12. Reports Hub & Bank Transfer Sheets | 6 | 4 | 2 | Ready
|  | 13. Audit Trails & System Logs | 4 | 2 | 2 | Ready
|  | 14. SuperAdmin Control & User Provisioning | 5 | 4 | 1 | Ready
|  | TOTAL TEST CASES |  |  |  | 88 Tests

## All System Test Cases
SHINEX HRIS & PAYROLL - MASTER UAT TEST CASE REPOSITORY
Complete end-to-end test execution matrix covering all 14 system functional modules
Test Case ID | Module | Sub-Module | Test Scenario / Title | Pre-Conditions | Step-by-Step Test Procedure | Test Input / Data | Expected Result | Actual Result | Status | Priority | Tested By | Date Tested | Remarks / Defect ID
TC-AUTH-001 | Authentication | Login | SuperAdmin Login with Valid Credentials | System is running, superadmin user seeded | 1. Navigate to /login 2. Enter Username: superadmin, Password: 123 3. Click Sign In | Username: superadmin, Password: 123 | User authenticated successfully, JWT token stored, redirected to Dashboard (/) |  | Untested | High
TC-AUTH-002 | Authentication | Login | Login with Invalid Password | System running on /login | 1. Enter Username: superadmin, Password: wrongpassword 2. Click Sign In | Username: superadmin, Password: wrongpassword | Error message displayed: 'Invalid credentials', stays on /login |  | Untested | High
TC-AUTH-003 | Authentication | Session | Session Token Persistence on Page Reload | User is logged in | 1. Refresh the browser (F5) 2. Navigate directly to /employees | Active token in localStorage | User remains logged in without being redirected back to /login |  | Untested | Medium
TC-AUTH-004 | Authentication | RBAC | Read-Only User Write Protection | User logged in with READ_ONLY role | 1. Attempt to add or edit any master record or employee 2. Click Save | Read-Only user account | System prevents modification and shows alert: 'Your account is read-only' |  | Untested | High
TC-AUTH-005 | Authentication | Logout | User Logout and Token Invalidation | User logged in | 1. Click user avatar/logout button in header 2. Confirm logout | Click Logout | Token cleared from storage, redirected to /login, back button does not open protected pages |  | Untested | High
TC-DASH-001 | Dashboard | Scope Switcher | Switch Active Business Center Scope | SuperAdmin logged in | 1. Click Business Center dropdown in top bar 2. Select '001 / Shinex Main' 3. Observe metric counts | Select BC 001 | Active scope changes to '001'; metric cards filter data to BC 001 only |  | Untested | High
TC-DASH-002 | Dashboard | Scope Switcher | Switch Scope to 'ALL Business Centers' | SuperAdmin logged in | 1. Click Business Center dropdown 2. Select 'ALL / All Business Centers' | Select ALL | Metrics display aggregated counts across all organizational units |  | Untested | High
TC-DASH-003 | Dashboard | Metrics | Employee & Attendance Counter Accuracy | Employees & attendance records exist | 1. View Total Employees metric 2. Cross check with Employees list total | Dashboard view | Count matches total active records in database |  | Untested | Medium
TC-DASH-004 | Dashboard | Navigation | Top Navigation Bar Module Links | Logged in user | 1. Click each link in top menu (Employees, Attendance, Masters, Reports, Admin) | Click menu items | Routes load rapidly without 404s or console errors |  | Untested | Medium
TC-SEC-001 | Sections Master | Code Auto-Gen | Section Code Auto-Generation on Load | Navigate to /sections | 1. Open Employee Sections page 2. Check Code input field | Page Load | Code field displays next sequence code (e.g. 001/006/024) with 'Auto-generated' badge |  | Untested | High
TC-SEC-002 | Sections Master | Autocomplete | Section Name Autocomplete Dropdown | On /sections form | 1. Focus Section Name input 2. Type 'Pack' 3. Click 'Packing Floor' from dropdown | Type 'Pack' | Dropdown opens displaying matching suggestions; clicking populates Section Name |  | Untested | High
TC-SEC-003 | Sections Master | Validation | Flexible Section Name Input (Case & Symbols) | On /sections form | 1. Type 'QC & QA Unit - 02' 2. Ensure no format errors trigger | Name: QC & QA Unit - 02 | Accepts mixed case, numbers, and special characters cleanly |  | Untested | Medium
TC-SEC-004 | Sections Master | Create | Add Section with Basic Salary & Business Center | On /sections form | 1. Name: 'Cutting Floor' 2. BC: '001' 3. Basic Salary: '45000' 4. Click Add Section | Name: Cutting Floor, BC: 001, Salary: 45000 | Section created successfully; DataTable shows formatted salary 'Rs. 45,000.00' |  | Untested | High
TC-SEC-005 | Sections Master | Search | Case-Insensitive DataTable Search | Sections created in table | 1. In search box, type 'cutting' 2. Clear and type 'CUTTING' 3. Clear and type '45000' | Search terms: cutting, CUTTING, 45000 | Matching records displayed instantly regardless of casing |  | Untested | Medium
TC-SEC-006 | Sections Master | Edit | Edit Section Basic Salary & Name | Existing section in table | 1. Click Edit icon on 'Cutting Floor' 2. Code is locked (disabled) 3. Change Salary to '48000' 4. Click Save Changes | Salary: 48000 | Record updated; DataTable immediately reflects new salary 'Rs. 48,000.00' |  | Untested | High
TC-SEC-007 | Sections Master | Auto-Code Reset | Code Auto-Refreshes on Business Center Change | On /sections Add form | 1. Change Business Center from 001 to 002 2. Verify Code updates | Change BC dropdown | Code calculates next available code for BC 002 |  | Untested | Medium
TC-SEC-008 | Sections Master | Auto-Salary Suggestion | Section Name Select Auto-fills Preset Salary | Preset section with salary exists | 1. In Section Name, select preset 'Packing Floor (Preset Rs. 45,000)' | Select preset | Basic Salary input automatically populates with 45000.00 |  | Untested | High
TC-SEC-009 | Sections Master | Delete | Delete Section with Confirmation | Existing section without linked employees | 1. Click Delete (trash) icon 2. Confirm in modal dialog | Confirm Delete | Section removed from table and database; success toast shown |  | Untested | High
TC-SEC-010 | Sections Master | Integrity | Delete Section Prevented if Employees Linked | Section assigned to active employee | 1. Attempt to delete section linked to employees | Delete linked section | System prevents deletion or shows dependency warning |  | Untested | High
TC-BC-001 | Business Centers | Create | Add New Business Center | Navigate to /business-centers | 1. Code: '003', Name: 'Shinex Galle Branch', Address: 'Galle Fort' 2. Click Add | Code: 003, Name: Shinex Galle | Business Center added and appears in Top Bar Scope switcher |  | Untested | High
TC-BC-002 | Business Centers | Edit | Edit Business Center Details | Existing Business Center | 1. Click Edit on '003' 2. Update address 3. Save | Address update | Updated successfully in database |  | Untested | Medium
TC-CUS-001 | Customers / Plants | Create | Add Customer / Plant with Working Days & OT Settings | Navigate to /customers | 1. Code: 'PL-01', Name: 'Factory North', Working Days: '26', Auto OT: 'Yes' 2. Click Save | Code: PL-01, Days: 26 | Plant registered and available in Employee & Attendance dropdowns |  | Untested | High
TC-CUS-002 | Customers / Plants | Allowance | Configure Attendance Allowance Rule on Plant | On /customers | 1. Check 'Attendance Allowance' 2. Min Days for Allowance: '24' 3. Save | Min Days: 24 | Rule saved and applied during monthly payroll calculation |  | Untested | High
TC-CUS-003 | Customers / Plants | Search | Search Plants by Code or Customer Name | Plants in DataTable | 1. Type plant code or partial name in search bar | Search: Factory | Table filters instantly |  | Untested | Low
TC-CUS-004 | Customers / Plants | Delete | Delete Unlinked Customer Plant | Plant without active logs | 1. Click delete & confirm | Confirm Delete | Plant deleted cleanly |  | Untested | Medium
TC-MST-001 | Additions Master | Create | Add Master Addition Type (Fixed / Variable) | Navigate to /additions | 1. Code: 'ATT_BONUS', Name: 'Attendance Bonus', Type: 'Fixed' 2. Click Add | Code: ATT_BONUS | Addition master type created and selectable in employee transactions |  | Untested | High
TC-MST-002 | Additions Master | EPF Flag | Configure EPF Qualifying Flag on Addition | On /additions | 1. Toggle 'Subject to EPF/ETF' on addition 2. Save | EPF Toggle: True | Flag saved; payroll engine includes this addition in EPF gross earnings |  | Untested | High
TC-MST-003 | Deductions Master | Create | Add Master Deduction Type (Welfare / Advance) | Navigate to /deductions | 1. Code: 'WELFARE', Name: 'Staff Welfare Society', Type: 'Fixed' 2. Click Add | Code: WELFARE | Deduction created and available in deduction transaction entry |  | Untested | High
TC-MST-004 | Deductions Master | Edit | Edit Deduction Description and Limits | Existing deduction | 1. Edit deduction details 2. Save | Description update | Updated in database and UI |  | Untested | Medium
TC-MST-005 | B-Cards Master | Create | Register B-Card for EPF Identification | Navigate to /bcards | 1. Enter B-Card No, Employee EPF No, Issue Date 2. Save | B-Card No: BC-9901 | B-Card linked to employee profile |  | Untested | Medium
TC-MST-006 | B-Cards Master | Search | Search B-Card by Card No or EPF No | B-Cards table | 1. Type EPF or Card No in search | Search: BC-9901 | Filters matching B-Card record |  | Untested | Low
TC-EMP-001 | Employees | Auto EPF | Auto-Generated EPF Number on Add Employee | Navigate to /employees | 1. Click '+ Add Employee' 2. Observe EPF No field | Add Employee | EPF No is auto-generated in sequence (e.g. 91EPF001) and locked against duplicate entry |  | Untested | High
TC-EMP-002 | Employees | DOB & Age | Auto-Calculate Age from Date of Birth | In Add Employee drawer | 1. Select Date of Birth: '1995-05-15' 2. Check Age field | DOB: 1995-05-15 | Age field automatically displays correct age (e.g. '31 years') in read-only input |  | Untested | Medium
TC-EMP-003 | Employees | Section Select | Searchable Section Dropdown Selection | In Add Employee drawer | 1. In Section field, type 'Cut' 2. Observe dropdown results 3. Click 'Cutting Floor' | Search: 'Cut' | SearchableSectionSelect filters matching sections with code badge, name, and preset salary |  | Untested | High
TC-EMP-004 | Employees | Salary Auto-fill | Auto-Populate Basic Salary from Selected Section | In Add Employee drawer | 1. Select section 'Cutting Floor' (which has preset salary 48000) 2. Scroll to Compensation | Section: Cutting Floor | Basic Salary under Compensation is automatically filled with 48000.00 |  | Untested | High
TC-EMP-005 | Employees | Salary Override | Manual Basic Salary Override for Custom Agreement | In Add Employee drawer | 1. With section selected, change Basic Salary from 48000 to 52000 2. Save employee | Salary: 52000 | Employee is saved with 52,000.00; section preset does not overwrite user entry |  | Untested | High
TC-EMP-006 | Employees | Hired Month | Auto-Calculate Hired Month from Hired Date | In Add Employee drawer | 1. Select Hired Date: '2026-03-10' 2. Check Hired Month dropdown | Hired Date: 2026-03-10 | Hired Month auto-selects 'March' with 'Auto-generated' badge |  | Untested | Medium
TC-EMP-007 | Employees | Allowances | Save Day, Night & Sunday Allowances | In Add Employee drawer | 1. Day Allowance: 500, Night Allowance: 800, Sunday Extra: 1200 2. Save | Allowances: 500/800/1200 | Allowances saved and displayed in employee compensation profile |  | Untested | High
TC-EMP-008 | Employees | Banking | Save Bank Details (Bank, Branch, Account, SWIFT) | In Add Employee drawer | 1. Bank Name: 'Commercial Bank', Branch: 'Colombo 03', Acc: '8001234567' 2. Save | Bank Info | Bank info saved; validateNameField prevents numeric bank names |  | Untested | Medium
TC-EMP-009 | Employees | Edit | Edit Existing Employee Profile | On /employees table | 1. Click Edit icon on employee 2. Modify address/phone 3. Click Save | Update Address | Changes saved; table updates immediately without page reload |  | Untested | High
TC-EMP-010 | Employees | Delete | Delete Employee with Confirmation Dialog | On /employees table | 1. Click Delete icon on employee 2. Confirm in modal | Confirm Delete | Employee deleted; record count decrements |  | Untested | High
TC-ATT-001 | Attendance | Entry | Record Daily Attendance (Day Shift / Normal Day) | Navigate to /attendance | 1. Select Date, Plant, and Employee 2. Shift: 'Day', Day Type: 'Normal' 3. In Time: 08:00, Out Time: 17:00 4. Save | Date: Today, Hours: 9 | Attendance logged with 8 Normal Hours + 1 Lunch hour deducted |  | Untested | High
TC-ATT-002 | Attendance | Night Shift | Record Night Shift Attendance with Night Allowance | On /attendance | 1. Select Shift: 'Night' 2. In: 20:00, Out: 05:00 3. Save | Shift: Night | Night shift recorded; Night allowance flagged for payroll calculation |  | Untested | High
TC-ATT-003 | Attendance | OT Hours | Calculate Overtime (Normal OT & Double OT) | On /attendance | 1. Out Time set to 20:00 (3 OT hours) 2. Sunday/Poya checked | 3 OT Hours on Sunday | OT Hours calculated correctly with Sunday multiplier rate |  | Untested | High
TC-ATT-004 | Attendance | Day Types | Poya / Special Holiday Day Type Handling | On /attendance | 1. Select Day Type: 'Poya Day' 2. Log attendance | Day Type: Poya | Applies Poya special pay rate in compensation snapshot |  | Untested | High
TC-ATT-005 | Attendance | Meal Allowance | Meal Allowance & Extra Allowance Toggles | On /attendance | 1. Toggle 'Meal Provided' / 'Meal Allowance' 2. Save | Meal: True | Meal allowance added to daily breakdown |  | Untested | Medium
TC-ATT-006 | Attendance | Bulk Sync | Bulk Attendance Upload / Summary Sync | On /attendance | 1. Click 'Sync Monthly Summary' 2. Select Month/Year | Month: September 2026 | Calculates total present days, leaves, and OT hours for all employees |  | Untested | High
TC-ATT-007 | Attendance | Search | Filter Attendance Records by Date & Plant | On /attendance history | 1. Filter by Date Range and Plant 'PL-01' | Plant PL-01 | Table shows attendance for selected plant only |  | Untested | Medium
TC-ATT-008 | Attendance | Lock | Prevent Edits on Finalized Attendance Month | Month finalized in Payroll | 1. Attempt to edit attendance in locked month | Locked Month | System displays 'Attendance is locked for finalized payroll period' |  | Untested | High
TC-TXN-001 | Additions Entry | Assign | Assign Monthly Fixed Addition to Employee | Navigate to /employee-additions | 1. Select Employee, Addition Type: 'ATT_BONUS', Amount: '5000', Month: 'September 2026' 2. Save | Amount: 5000 | Addition added to employee's monthly payroll slip |  | Untested | High
TC-TXN-002 | Additions Entry | Recurring | Set Recurring Addition across Months | On /employee-additions | 1. Select 'Recurring' checkbox 2. Save | Recurring: Yes | Addition automatically carries over into subsequent monthly runs |  | Untested | Medium
TC-TXN-003 | Additions Entry | Delete | Delete / Revoke Assigned Addition | On /employee-additions table | 1. Delete entry 2. Confirm | Delete | Addition removed from calculation |  | Untested | Medium
TC-TXN-004 | Deductions Entry | Assign | Assign Salary Advance / Monthly Deduction | Navigate to /employee-deductions | 1. Select Employee, Deduction: 'ADVANCE', Amount: '10000', Month: 'September 2026' 2. Save | Amount: 10000 | Deduction recorded and deducted from net pay |  | Untested | High
TC-TXN-005 | Deductions Entry | Limit Check | Deduction Exceeding Maximum Limit Warning | On /employee-deductions | 1. Enter deduction amount greater than employee basic salary | Excessive Amount | Warning displayed: 'Deduction exceeds net pay threshold' |  | Untested | High
TC-TXN-006 | Deductions Entry | Search | Filter Deductions by Employee EPF & Month | On /employee-deductions | 1. Search by EPF in search bar | EPF: 91EPF001 | Displays deduction breakdown for selected employee |  | Untested | Low
TC-LEV-001 | Leaves | Apply | Submit Leave Request (Annual / Casual / Medical) | Navigate to /leaves | 1. Select Employee, Leave Type: 'AL', Start: '2026-09-10', End: '2026-09-12' 2. Submit | 3 Days AL | Leave request logged; Days calculated as 3; Status: 'Pending' or 'Approved' |  | Untested | High
TC-LEV-002 | Leaves | No Pay | No Pay Leave (NOP) Salary Deduction | On /leaves | 1. Apply 2 days 'NOP' leave 2. Check Monthly Breakdown | 2 Days NOP | Payroll engine deducts 2 days proportionate basic salary as No Pay |  | Untested | High
TC-LEV-003 | Leaves | Balance | Leave Balance Decrement Validation | On /leaves | 1. Check remaining Annual Leave balance after approval | AL Balance check | Remaining AL balance decreases by approved leave days |  | Untested | Medium
TC-LON-001 | Loans | Issue | Issue Employee Loan with Monthly Installments | Navigate to /loans | 1. Employee: 91EPF001, Principal: '60000', Installments: '12', Monthly Deduct: '5000' 2. Save | Principal: 60000, 12 months | Loan created; Monthly deduction scheduled for next 12 payroll runs |  | Untested | High
TC-LON-002 | Loans | Recovery | Automatic Loan Installment Deduction during Payroll | Run monthly payroll | 1. Process payroll for month with active loan | Payroll Run | Net salary deducts 5,000.00; Outstanding loan balance updates to 55,000.00 |  | Untested | High
TC-LON-003 | Loans | Settlement | Early Full Loan Settlement | On /loans | 1. Click 'Settle Loan' 2. Enter settlement amount 3. Confirm | Full Settlement | Loan status marks 'Settled'; future automatic deductions cease |  | Untested | Medium
TC-TRN-001 | Plant Transfers | Transfer | Transfer Employee from Plant A to Plant B | Navigate to /plant-transfers | 1. Select Employee, From Plant: 'PL-01', To Plant: 'PL-02', Effective Date: '2026-09-15' 2. Save | To Plant: PL-02 | Employee's active plant updates on effective date |  | Untested | High
TC-TRN-002 | Plant Transfers | Attendance | Attendance Routing Post-Transfer | Employee transferred | 1. Log attendance on Plant PL-02 after effective date | PL-02 Attendance | Attendance is recorded and billed under the new plant |  | Untested | High
TC-TRN-003 | Plant Transfers | History | Employee History Reflects Transfer Timeline | Navigate to /employee-history | 1. Open transferred employee history profile | View History | Transfer event displayed in chronological audit timeline |  | Untested | Medium
TC-TRN-004 | Plant Transfers | Cancel | Cancel / Revert Scheduled Transfer | Transfer with future date | 1. Click Cancel Transfer | Cancel Transfer | Employee remains on original plant |  | Untested | Low
TC-PAY-001 | Payroll Engine | Calculate | Run Monthly Payroll Calculation for Business Center | Navigate to /monthly-breakdown | 1. Select Month: 'September 2026', BC: '001' 2. Click 'Process Payroll' | Process Month: Sep 2026 | Calculates Gross Pay, EPF 8%, EPF 12%, ETF 3%, Total Additions, Deductions, and Net Pay for all employees |  | Untested | High
TC-PAY-002 | Payroll Engine | EPF/ETF | Statutory EPF (8% & 12%) and ETF (3%) Accuracy | In Payroll Breakdown | 1. Check Employee with Basic Salary 50,000 2. Verify EPF Employee: 4,000 (8%) 3. Verify EPF Employer: 6,000 (12%) 4. Verify ETF Employer: 1,500 (3%) | Basic: 50,000 | All statutory calculations match exact decimal percentages (8%, 12%, 3%) |  | Untested | High
TC-PAY-003 | Payroll Engine | OT Pay | Overtime Earnings Integration into Gross Pay | Employee has 10 OT hours | 1. Cross check OT hours in payroll summary | 10 OT Hours | OT amount calculated at (Basic / 200 * 1.5 * OT_Hours) and added to Gross |  | Untested | High
TC-PAY-004 | Payroll Engine | Attendance Bonus | Attendance Allowance Qualification | Employee worked >= 24 days | 1. Check Attendance Allowance column | Present Days >= 24 | Allowance added if criteria met; excluded if present days < min threshold |  | Untested | High
TC-PAY-005 | Payroll Engine | Death Donation | Death Donation Deduction Processing | Employee has death donation checked | 1. Verify Death Donation line item in breakdown | Death Donation: True | Fixed death donation amount deducted from net pay |  | Untested | Medium
TC-PAY-006 | Payroll Engine | Payslip View | View Individual Employee Digital Payslip | In /monthly-breakdown table | 1. Click 'View Payslip' icon on employee row | View Payslip | Modal opens displaying full earnings, statutory deductions, loan recoveries, and Net Pay |  | Untested | High
TC-PAY-007 | Payroll Engine | Print / PDF | Export / Print Employee Payslip | In Payslip modal | 1. Click 'Print Payslip' or 'Export PDF' | Print Action | Clean printable payslip generated formatted for standard A4/thermal printing |  | Untested | High
TC-PAY-008 | Payroll Engine | Finalize | Finalize & Lock Monthly Payroll Period | In /monthly-breakdown | 1. Click 'Finalize Month' 2. Confirm lock | Finalize Month | Month marked LOCKED; prevents further retroactive attendance/addition changes |  | Untested | High
TC-REP-001 | Reports Hub | Salary Sheet | Generate Monthly Master Salary Sheet Report | Navigate to /reports | 1. Select 'Monthly Master Salary Sheet', Month: 'Sep 2026', BC: '001' 2. Generate | Salary Sheet | Comprehensive table with all employees, basic, allowances, OT, gross, EPF/ETF, net pay |  | Untested | High
TC-REP-002 | Reports Hub | EPF C-Form | Generate Monthly EPF C-Form & Return Statement | On /reports | 1. Select 'EPF Monthly Statement (C-Form)' 2. Click Generate | EPF C-Form | Displays EPF member numbers, NIC, gross earnings, 8% employee contribution, 12% employer |  | Untested | High
TC-REP-003 | Reports Hub | ETF Form | Generate Monthly ETF Contribution Statement | On /reports | 1. Select 'ETF Monthly Statement' 2. Generate | ETF Statement | Displays 3% employer contribution breakdown by employee |  | Untested | High
TC-REP-004 | Reports Hub | Bank File | Generate Bank Transfer (SLIPS / Excel / Text) File | On /reports | 1. Select 'Bank Transfer Export', Select Bank: 'Commercial Bank' 2. Export | Bank Export | Generates bank transfer format with Account No, Name, and Net Salary amount |  | Untested | High
TC-REP-005 | Reports Hub | Attendance Rep | Generate Plant-wise Monthly Attendance Summary | On /reports | 1. Select 'Plant Attendance Summary', Plant: 'PL-01' 2. Generate | Plant PL-01 Summary | Displays days worked, total OT hours, leaves, and absentees per plant |  | Untested | Medium
TC-REP-006 | Reports Hub | Export CSV | Export Any Generated Report to CSV / Excel | On report view | 1. Click 'Export to Excel' / 'Export CSV' | Export Action | File downloads immediately with complete table data |  | Untested | Medium
TC-AUD-001 | Audit Logs | Logging | Automatic Audit Trail on Master & Employee Changes | Perform create/update on Section or Employee | 1. Navigate to /audit-logs 2. Check latest log entries | View Logs | Log records Timestamp, Performed By (user), Action (CREATE/UPDATE/DELETE), and Entity ID |  | Untested | High
TC-AUD-002 | Audit Logs | Search | Filter Audit Logs by Module & User | On /audit-logs | 1. Filter by Module: 'SECTIONS' or 'EMPLOYEES' 2. Filter by User: 'superadmin' | Module: SECTIONS | Displays only actions matching the selected filter |  | Untested | Medium
TC-AUD-003 | Audit Logs | Date Range | Filter Audit Logs by Date Range | On /audit-logs | 1. Select From Date and To Date 2. Apply filter | Date Range | Table shows logs within the specified period |  | Untested | Low
TC-AUD-004 | Audit Logs | Immutability | Audit Logs Read-Only Immutability | On /audit-logs | 1. Verify no delete/edit action buttons exist on audit log records | Immutability Check | Audit logs are strictly append-only and cannot be altered or deleted |  | Untested | High
TC-ADM-001 | Admin Control | Create User | Create New System User Account | Logged in as SuperAdmin on /admin-control | 1. Enter Username: 'hr_manager', Role: 'ADMIN', BC: '001', Password: 'Password@123' 2. Click Create | User: hr_manager | User account created; appears in User List table |  | Untested | High
TC-ADM-002 | Admin Control | Role Assign | Assign Role & Access Level (SUPERADMIN / ADMIN / USER / READ_ONLY) | On /admin-control | 1. Select Role: 'READ_ONLY' 2. Save user | Role: READ_ONLY | User permissions restrict write actions across all forms |  | Untested | High
TC-ADM-003 | Admin Control | BC Scope | Assign Dedicated Business Center Scope to User | On /admin-control | 1. Set User Scope to '002' 2. Log in with this user | User Scope: 002 | User can only access data isolated to Business Center 002 |  | Untested | High
TC-ADM-004 | Admin Control | Block User | Block / Deactivate User Account | On /admin-control | 1. Toggle 'Blocked' on user account 2. Attempt login with that user | Blocked user login | Login rejected with message: 'Account is deactivated. Contact Administrator' |  | Untested | High
TC-ADM-005 | Admin Control | Password Reset | SuperAdmin Reset Password for User Account | On /admin-control | 1. Click 'Reset Password' on user 2. Enter new password 3. Save | New Password | User can successfully sign in with the new password |  | Untested | Medium

## Employee & Sections UAT
EMPLOYEE SECTIONS & COMPENSATION AUTO-FILL UAT
Focused acceptance tests for Section Code Auto-Gen, Name Autocomplete, BC Isolation, and Basic Salary Auto-Fill
Test Case ID | Module | Sub-Module | Test Scenario / Title | Pre-Conditions | Step-by-Step Test Procedure | Test Input / Data | Expected Result | Actual Result | Status | Priority | Tested By | Date Tested | Remarks / Defect ID
TC-SEC-001 | Sections Master | Code Auto-Gen | Section Code Auto-Generation on Load | Navigate to /sections | 1. Open Employee Sections page 2. Check Code input field | Page Load | Code field displays next sequence code (e.g. 001/006/024) with 'Auto-generated' badge |  | Untested | High
TC-SEC-002 | Sections Master | Autocomplete | Section Name Autocomplete Dropdown | On /sections form | 1. Focus Section Name input 2. Type 'Pack' 3. Click 'Packing Floor' from dropdown | Type 'Pack' | Dropdown opens displaying matching suggestions; clicking populates Section Name |  | Untested | High
TC-SEC-003 | Sections Master | Validation | Flexible Section Name Input (Case & Symbols) | On /sections form | 1. Type 'QC & QA Unit - 02' 2. Ensure no format errors trigger | Name: QC & QA Unit - 02 | Accepts mixed case, numbers, and special characters cleanly |  | Untested | Medium
TC-SEC-004 | Sections Master | Create | Add Section with Basic Salary & Business Center | On /sections form | 1. Name: 'Cutting Floor' 2. BC: '001' 3. Basic Salary: '45000' 4. Click Add Section | Name: Cutting Floor, BC: 001, Salary: 45000 | Section created successfully; DataTable shows formatted salary 'Rs. 45,000.00' |  | Untested | High
TC-SEC-005 | Sections Master | Search | Case-Insensitive DataTable Search | Sections created in table | 1. In search box, type 'cutting' 2. Clear and type 'CUTTING' 3. Clear and type '45000' | Search terms: cutting, CUTTING, 45000 | Matching records displayed instantly regardless of casing |  | Untested | Medium
TC-SEC-006 | Sections Master | Edit | Edit Section Basic Salary & Name | Existing section in table | 1. Click Edit icon on 'Cutting Floor' 2. Code is locked (disabled) 3. Change Salary to '48000' 4. Click Save Changes | Salary: 48000 | Record updated; DataTable immediately reflects new salary 'Rs. 48,000.00' |  | Untested | High
TC-SEC-007 | Sections Master | Auto-Code Reset | Code Auto-Refreshes on Business Center Change | On /sections Add form | 1. Change Business Center from 001 to 002 2. Verify Code updates | Change BC dropdown | Code calculates next available code for BC 002 |  | Untested | Medium
TC-SEC-008 | Sections Master | Auto-Salary Suggestion | Section Name Select Auto-fills Preset Salary | Preset section with salary exists | 1. In Section Name, select preset 'Packing Floor (Preset Rs. 45,000)' | Select preset | Basic Salary input automatically populates with 45000.00 |  | Untested | High
TC-SEC-009 | Sections Master | Delete | Delete Section with Confirmation | Existing section without linked employees | 1. Click Delete (trash) icon 2. Confirm in modal dialog | Confirm Delete | Section removed from table and database; success toast shown |  | Untested | High
TC-SEC-010 | Sections Master | Integrity | Delete Section Prevented if Employees Linked | Section assigned to active employee | 1. Attempt to delete section linked to employees | Delete linked section | System prevents deletion or shows dependency warning |  | Untested | High
TC-EMP-001 | Employees | Auto EPF | Auto-Generated EPF Number on Add Employee | Navigate to /employees | 1. Click '+ Add Employee' 2. Observe EPF No field | Add Employee | EPF No is auto-generated in sequence (e.g. 91EPF001) and locked against duplicate entry |  | Untested | High
TC-EMP-002 | Employees | DOB & Age | Auto-Calculate Age from Date of Birth | In Add Employee drawer | 1. Select Date of Birth: '1995-05-15' 2. Check Age field | DOB: 1995-05-15 | Age field automatically displays correct age (e.g. '31 years') in read-only input |  | Untested | Medium
TC-EMP-003 | Employees | Section Select | Searchable Section Dropdown Selection | In Add Employee drawer | 1. In Section field, type 'Cut' 2. Observe dropdown results 3. Click 'Cutting Floor' | Search: 'Cut' | SearchableSectionSelect filters matching sections with code badge, name, and preset salary |  | Untested | High
TC-EMP-004 | Employees | Salary Auto-fill | Auto-Populate Basic Salary from Selected Section | In Add Employee drawer | 1. Select section 'Cutting Floor' (which has preset salary 48000) 2. Scroll to Compensation | Section: Cutting Floor | Basic Salary under Compensation is automatically filled with 48000.00 |  | Untested | High
TC-EMP-005 | Employees | Salary Override | Manual Basic Salary Override for Custom Agreement | In Add Employee drawer | 1. With section selected, change Basic Salary from 48000 to 52000 2. Save employee | Salary: 52000 | Employee is saved with 52,000.00; section preset does not overwrite user entry |  | Untested | High
TC-EMP-006 | Employees | Hired Month | Auto-Calculate Hired Month from Hired Date | In Add Employee drawer | 1. Select Hired Date: '2026-03-10' 2. Check Hired Month dropdown | Hired Date: 2026-03-10 | Hired Month auto-selects 'March' with 'Auto-generated' badge |  | Untested | Medium
TC-EMP-007 | Employees | Allowances | Save Day, Night & Sunday Allowances | In Add Employee drawer | 1. Day Allowance: 500, Night Allowance: 800, Sunday Extra: 1200 2. Save | Allowances: 500/800/1200 | Allowances saved and displayed in employee compensation profile |  | Untested | High
TC-EMP-008 | Employees | Banking | Save Bank Details (Bank, Branch, Account, SWIFT) | In Add Employee drawer | 1. Bank Name: 'Commercial Bank', Branch: 'Colombo 03', Acc: '8001234567' 2. Save | Bank Info | Bank info saved; validateNameField prevents numeric bank names |  | Untested | Medium
TC-EMP-009 | Employees | Edit | Edit Existing Employee Profile | On /employees table | 1. Click Edit icon on employee 2. Modify address/phone 3. Click Save | Update Address | Changes saved; table updates immediately without page reload |  | Untested | High
TC-EMP-010 | Employees | Delete | Delete Employee with Confirmation Dialog | On /employees table | 1. Click Delete icon on employee 2. Confirm in modal | Confirm Delete | Employee deleted; record count decrements |  | Untested | High

## Attendance & Payroll UAT
DAILY ATTENDANCE, TRANSACTIONS & PAYROLL PROCESSING UAT
Testing daily time-tracking, additions/deductions, leaves, loans, and monthly salary engine
Test Case ID | Module | Sub-Module | Test Scenario / Title | Pre-Conditions | Step-by-Step Test Procedure | Test Input / Data | Expected Result | Actual Result | Status | Priority | Tested By | Date Tested | Remarks / Defect ID
TC-ATT-001 | Attendance | Entry | Record Daily Attendance (Day Shift / Normal Day) | Navigate to /attendance | 1. Select Date, Plant, and Employee 2. Shift: 'Day', Day Type: 'Normal' 3. In Time: 08:00, Out Time: 17:00 4. Save | Date: Today, Hours: 9 | Attendance logged with 8 Normal Hours + 1 Lunch hour deducted |  | Untested | High
TC-ATT-002 | Attendance | Night Shift | Record Night Shift Attendance with Night Allowance | On /attendance | 1. Select Shift: 'Night' 2. In: 20:00, Out: 05:00 3. Save | Shift: Night | Night shift recorded; Night allowance flagged for payroll calculation |  | Untested | High
TC-ATT-003 | Attendance | OT Hours | Calculate Overtime (Normal OT & Double OT) | On /attendance | 1. Out Time set to 20:00 (3 OT hours) 2. Sunday/Poya checked | 3 OT Hours on Sunday | OT Hours calculated correctly with Sunday multiplier rate |  | Untested | High
TC-ATT-004 | Attendance | Day Types | Poya / Special Holiday Day Type Handling | On /attendance | 1. Select Day Type: 'Poya Day' 2. Log attendance | Day Type: Poya | Applies Poya special pay rate in compensation snapshot |  | Untested | High
TC-ATT-005 | Attendance | Meal Allowance | Meal Allowance & Extra Allowance Toggles | On /attendance | 1. Toggle 'Meal Provided' / 'Meal Allowance' 2. Save | Meal: True | Meal allowance added to daily breakdown |  | Untested | Medium
TC-ATT-006 | Attendance | Bulk Sync | Bulk Attendance Upload / Summary Sync | On /attendance | 1. Click 'Sync Monthly Summary' 2. Select Month/Year | Month: September 2026 | Calculates total present days, leaves, and OT hours for all employees |  | Untested | High
TC-ATT-007 | Attendance | Search | Filter Attendance Records by Date & Plant | On /attendance history | 1. Filter by Date Range and Plant 'PL-01' | Plant PL-01 | Table shows attendance for selected plant only |  | Untested | Medium
TC-ATT-008 | Attendance | Lock | Prevent Edits on Finalized Attendance Month | Month finalized in Payroll | 1. Attempt to edit attendance in locked month | Locked Month | System displays 'Attendance is locked for finalized payroll period' |  | Untested | High
TC-TXN-001 | Additions Entry | Assign | Assign Monthly Fixed Addition to Employee | Navigate to /employee-additions | 1. Select Employee, Addition Type: 'ATT_BONUS', Amount: '5000', Month: 'September 2026' 2. Save | Amount: 5000 | Addition added to employee's monthly payroll slip |  | Untested | High
TC-TXN-002 | Additions Entry | Recurring | Set Recurring Addition across Months | On /employee-additions | 1. Select 'Recurring' checkbox 2. Save | Recurring: Yes | Addition automatically carries over into subsequent monthly runs |  | Untested | Medium
TC-TXN-003 | Additions Entry | Delete | Delete / Revoke Assigned Addition | On /employee-additions table | 1. Delete entry 2. Confirm | Delete | Addition removed from calculation |  | Untested | Medium
TC-TXN-004 | Deductions Entry | Assign | Assign Salary Advance / Monthly Deduction | Navigate to /employee-deductions | 1. Select Employee, Deduction: 'ADVANCE', Amount: '10000', Month: 'September 2026' 2. Save | Amount: 10000 | Deduction recorded and deducted from net pay |  | Untested | High
TC-TXN-005 | Deductions Entry | Limit Check | Deduction Exceeding Maximum Limit Warning | On /employee-deductions | 1. Enter deduction amount greater than employee basic salary | Excessive Amount | Warning displayed: 'Deduction exceeds net pay threshold' |  | Untested | High
TC-TXN-006 | Deductions Entry | Search | Filter Deductions by Employee EPF & Month | On /employee-deductions | 1. Search by EPF in search bar | EPF: 91EPF001 | Displays deduction breakdown for selected employee |  | Untested | Low
TC-LEV-001 | Leaves | Apply | Submit Leave Request (Annual / Casual / Medical) | Navigate to /leaves | 1. Select Employee, Leave Type: 'AL', Start: '2026-09-10', End: '2026-09-12' 2. Submit | 3 Days AL | Leave request logged; Days calculated as 3; Status: 'Pending' or 'Approved' |  | Untested | High
TC-LEV-002 | Leaves | No Pay | No Pay Leave (NOP) Salary Deduction | On /leaves | 1. Apply 2 days 'NOP' leave 2. Check Monthly Breakdown | 2 Days NOP | Payroll engine deducts 2 days proportionate basic salary as No Pay |  | Untested | High
TC-LEV-003 | Leaves | Balance | Leave Balance Decrement Validation | On /leaves | 1. Check remaining Annual Leave balance after approval | AL Balance check | Remaining AL balance decreases by approved leave days |  | Untested | Medium
TC-LON-001 | Loans | Issue | Issue Employee Loan with Monthly Installments | Navigate to /loans | 1. Employee: 91EPF001, Principal: '60000', Installments: '12', Monthly Deduct: '5000' 2. Save | Principal: 60000, 12 months | Loan created; Monthly deduction scheduled for next 12 payroll runs |  | Untested | High
TC-LON-002 | Loans | Recovery | Automatic Loan Installment Deduction during Payroll | Run monthly payroll | 1. Process payroll for month with active loan | Payroll Run | Net salary deducts 5,000.00; Outstanding loan balance updates to 55,000.00 |  | Untested | High
TC-LON-003 | Loans | Settlement | Early Full Loan Settlement | On /loans | 1. Click 'Settle Loan' 2. Enter settlement amount 3. Confirm | Full Settlement | Loan status marks 'Settled'; future automatic deductions cease |  | Untested | Medium
TC-TRN-001 | Plant Transfers | Transfer | Transfer Employee from Plant A to Plant B | Navigate to /plant-transfers | 1. Select Employee, From Plant: 'PL-01', To Plant: 'PL-02', Effective Date: '2026-09-15' 2. Save | To Plant: PL-02 | Employee's active plant updates on effective date |  | Untested | High
TC-TRN-002 | Plant Transfers | Attendance | Attendance Routing Post-Transfer | Employee transferred | 1. Log attendance on Plant PL-02 after effective date | PL-02 Attendance | Attendance is recorded and billed under the new plant |  | Untested | High
TC-TRN-003 | Plant Transfers | History | Employee History Reflects Transfer Timeline | Navigate to /employee-history | 1. Open transferred employee history profile | View History | Transfer event displayed in chronological audit timeline |  | Untested | Medium
TC-TRN-004 | Plant Transfers | Cancel | Cancel / Revert Scheduled Transfer | Transfer with future date | 1. Click Cancel Transfer | Cancel Transfer | Employee remains on original plant |  | Untested | Low
TC-PAY-001 | Payroll Engine | Calculate | Run Monthly Payroll Calculation for Business Center | Navigate to /monthly-breakdown | 1. Select Month: 'September 2026', BC: '001' 2. Click 'Process Payroll' | Process Month: Sep 2026 | Calculates Gross Pay, EPF 8%, EPF 12%, ETF 3%, Total Additions, Deductions, and Net Pay for all employees |  | Untested | High
TC-PAY-002 | Payroll Engine | EPF/ETF | Statutory EPF (8% & 12%) and ETF (3%) Accuracy | In Payroll Breakdown | 1. Check Employee with Basic Salary 50,000 2. Verify EPF Employee: 4,000 (8%) 3. Verify EPF Employer: 6,000 (12%) 4. Verify ETF Employer: 1,500 (3%) | Basic: 50,000 | All statutory calculations match exact decimal percentages (8%, 12%, 3%) |  | Untested | High
TC-PAY-003 | Payroll Engine | OT Pay | Overtime Earnings Integration into Gross Pay | Employee has 10 OT hours | 1. Cross check OT hours in payroll summary | 10 OT Hours | OT amount calculated at (Basic / 200 * 1.5 * OT_Hours) and added to Gross |  | Untested | High
TC-PAY-004 | Payroll Engine | Attendance Bonus | Attendance Allowance Qualification | Employee worked >= 24 days | 1. Check Attendance Allowance column | Present Days >= 24 | Allowance added if criteria met; excluded if present days < min threshold |  | Untested | High
TC-PAY-005 | Payroll Engine | Death Donation | Death Donation Deduction Processing | Employee has death donation checked | 1. Verify Death Donation line item in breakdown | Death Donation: True | Fixed death donation amount deducted from net pay |  | Untested | Medium
TC-PAY-006 | Payroll Engine | Payslip View | View Individual Employee Digital Payslip | In /monthly-breakdown table | 1. Click 'View Payslip' icon on employee row | View Payslip | Modal opens displaying full earnings, statutory deductions, loan recoveries, and Net Pay |  | Untested | High
TC-PAY-007 | Payroll Engine | Print / PDF | Export / Print Employee Payslip | In Payslip modal | 1. Click 'Print Payslip' or 'Export PDF' | Print Action | Clean printable payslip generated formatted for standard A4/thermal printing |  | Untested | High
TC-PAY-008 | Payroll Engine | Finalize | Finalize & Lock Monthly Payroll Period | In /monthly-breakdown | 1. Click 'Finalize Month' 2. Confirm lock | Finalize Month | Month marked LOCKED; prevents further retroactive attendance/addition changes |  | Untested | High